## Template
Project Name:
Week Of
| 2020-11-01 | 2020-11-08 | 2020-11-15 | 2020-11-22 | 2020-11-29 | 2020-12-06 | 2020-12-13 | 2020-12-20 | 2020-12-27 | 2021-01-03 | 2021-01-10 | 2021-01-17 | 2021-01-24 | 2021-01-31 | 2021-02-07 | 2021-02-14 | 2021-02-21 | 2021-02-28 | 2021-03-07 | 2021-03-14 | 2021-03-21 | 2021-03-28 | 2021-04-04 | OWNER/S
Identify Project
Identify Core Planning Group
Prepare and Submit Application
Review and Sign MOU
Finalize Budget + Schedule
Identify Risks
Identify Permit/Permission Needs
Identify People Needs
Identify Materials
Plan for Risks
Secure Permit/Permissions
Outreach to People
Order/Buy/Collect Materials
Stage Materials/Project Needs
Project Day(s)
Celebrate!
Prepare and Submit Final Report

## Template - Blank
Project Name:
Week Of
| 2020-11-01 | 2020-11-08 | 2020-11-15 | 2020-11-22 | 2020-11-29 | 2020-12-06 | 2020-12-13 | 2020-12-20 | 2020-12-27 | 2021-01-03 | 2021-01-10 | 2021-01-17 | 2021-01-24 | 2021-01-31 | 2021-02-07 | 2021-02-14 | 2021-02-21 | 2021-02-28 | 2021-03-07 | 2021-03-14 | 2021-03-21 | 2021-03-28 | 2021-04-04 | OWNER/S

## Example
Project Name: | Project Porch Repairs
Week Of
| 2020-11-01 | 2020-11-08 | 2020-11-15 | 2020-11-22 | 2020-11-29 | 2020-12-06 | 2020-12-13 | 2020-12-20 | 2020-12-27 | 2021-01-03 | 2021-01-10 | 2021-01-17 | 2021-01-24 | 2021-01-31 | 2021-02-07 | 2021-02-14 | 2021-02-21 | 2021-02-28 | 2021-03-07 | 2021-03-14 | 2021-03-21 | 2021-03-28 | 2021-04-04 | OWNER/S
Identify Project | [23 empty] | Terrence, Abigail, Elizabeth, Jane, John
Identify Core Planning Group | [23 empty] | Terrence, Abigail, Elizabeth, Jane, John
Prepare and Submit Application | [23 empty] | Elizabeth + Terrence
Review and Sign MOU | [23 empty] | Elizabeth (with Core Group)
Finalize Budget + Schedule | [23 empty] | Elizabeth + Terrence (with Core Group)
Identify Risks | [23 empty] | John (with Core Group)
Identify Permit/Permission Needs | [23 empty] | John
Identify People Needs | [23 empty] | Core Group
Identify Materials | [23 empty] | Abigail
Plan for Risks | [23 empty] | John (with Core Group)
Secure Permit/Permission | [23 empty] | John
Outreach to People | [23 empty] | Core Group
Order/Buy/Collect Materials | [23 empty] | Abigail
Stage materials/project needs | [23 empty] | Terrence + Elizabeth
Project Day(s) | [23 empty] | All!
Celebrate! | [23 empty] | All!
Prepare and Submit Final Report | [23 empty] | Terrence (with Core Group)