## Example
Example timeline
Week Of:
| 2021-07-01 | 2021-07-08 | 2021-07-15 | 2021-07-22 | 2021-07-29 | 2021-08-05 | 2021-08-12 | 2021-08-19 | 2021-08-26 | 2021-09-02 | 2021-09-09 | 2021-09-16 | 2021-09-23 | 2021-09-30 | 2021-10-07 | 2021-10-14 | 2021-10-21 | OWNER/S
Identify Core Planning Group | [17 empty] | Whole Core Planning Group
Identify Project Idea | [17 empty] | Whole Core Planning Group
Research Project Needs | [17 empty] | Group members 1 + 2 (with input from Core Group)
Develop Project Timeline and Budget | [17 empty] | Team members 3 + 4 (with input from Core Group)
Prepare and Submit Application | [17 empty] | Team members 3 + 4 (with input from Core Group)
Review and Sign GAA | [17 empty] | Whole Core Planning Group
Finalize Budget + Schedule | [17 empty] | Team members 3 + 4 (with input from Core Group)
Identify and Plan for Risks | [17 empty] | Team member 5 (with input from Core Group)
Fufill Legal Requirements, if Present (Permit/Permission Needs) | [17 empty] | Team member 5
Identify Volunteers for Project | [17 empty] | Team members 1 + 2
Outreach to Community | [17 empty] | Team members 1 + 2
Order/Buy/Collect Materials | [17 empty] | Team member 3
Stage Materials/Project Needs (do a Practice Run of Event Logistics) | [17 empty] | Team members 3 + 4
Project Day(s) | [17 empty] | All!
Celebrate! | [17 empty] | All!
Prepare and Submit Final Report | [17 empty] | Team member 1 (with input from Core Group)

## Template
Blank timeline with example task list - fill in your dates and who will work on each task
Week Of:
| X/X | X/X | X/X | X/X | X/X | X/X | X/X | X/X | X/X | X/X | X/X | X/X | X/X | X/X | X/X | X/X | X/X | OWNER/S
Identify Core Planning Group
Identify Project Idea
Research Project Needs
Develop Project Timeline and Budget
Prepare and Submit Application
Review and Sign GAA
Finalize Budget + Schedule
Identify and Plan for Risks
Fufill Legal Requirements, if Present (Permit/Permission Needs)
Identify Volunteers for Project
Outreach to Community
Order/Buy/Collect Materials
Stage Materials/Project Needs (do a Practice Run of Event Logistics)
Project Day(s)
Celebrate!
Prepare and Submit Final Report

## Template Blank
Blank template - fill in your task list, dates, and who will work on each task
Project Name:
Week Of: | 2020-07-01 | 2020-07-08 | 2020-07-15 | 2020-07-22 | 2020-07-29 | 2020-08-05 | 2020-08-12 | 2020-08-19 | 2020-08-26 | 2020-09-02 | 2020-09-09 | 2020-09-16 | 2020-09-23 | 2020-09-30 | 2020-10-07 | 2020-10-14 | 2020-10-21 | OWNER/S
Some Ideas: Identify Project; Prepare and Submit Application; Review and Sign GAA; Finalize Budget + Schedule; Identify Risks; Identify Permit/Permission Needs; Identify People Needs; Identify Materials; Plan for Risks; Secure Permit/Permissions; Outreach to People; Order/Buy/Collect Materials; Stage materials/project needs; Project Day(s); Celebrate!; Prepare and Submit Final Report